## Summary
HSFP 1:50 Test Matrix – Summary
Target site: ~200 mi west of Seattle (deep Pacific, NDBC 46005 climate). Draft for TEAMER / HWRL scoping.
Phase | Configurations | Decay runs | Regular runs | Irregular runs | Special runs | Total runs | Tank hours | Tank days
Phase 1 – Individual buoys | 5 | 30 | 111 | 30 | 21 | 192 | 38.5553 | 6.4259
Phase 2 – Buoy clusters | 4 | 27 | 111 | 30 | 12 | 180 | 36.5053 | 6.0842
Phase 3 – Full platform | 6 | 27 | 144 | 45 | 14 | 230 | 54.0602 | 9.01
Total | 15 | 84 | 366 | 105 | 47 | 602 | 129.1207 | 21.5201
By facility
Facility | Configurations | Decay runs | Regular runs | Irregular runs | Special runs | Total runs | Tank hours | Tank days
Large Wave Flume (LWF) | 13 | 84 | 315 | 90 | 41 | 530 | 108.485 | 18.0808
Directional Wave Basin (DWB) | 2 | 0 | 51 | 15 | 6 | 72 | 20.6357 | 3.4393
Key points (confirm with HWRL – Pedro Lomonaco):
• Site depth (~2,500 m) cannot be reproduced at 1:50. LWF at 2.74 m (137 m FS) makes waves ≤13 s fully deep-water and 14–20 s near-deep (kd ≈ 1.5–2.9); it also keeps the published 1.8 m wave-height capability.
• Phase 3 baseline moved to the LWF: slender spars give low solid blockage, and the flume gives the deeper depth. The DWB (68 m FS) is used only for oblique headings and short-crested seas.
• Side-wall effects: cross-flume standing modes at ~7.7, 8.9, 10.9 and 15.5 s FS (see Inputs; 7.7 and 10.9 s are the symmetric modes most likely excited). Install a cross-flume wave-gauge pair and keep the model centred.
• Moorings: a ~2,500 m-deep site implies taut/synthetic moorings. The model needs a truncated mooring with equivalent horizontal stiffness – document the method.
• Extremes from NDBC 46005: 10/25/50/100-yr Hs = 12.4 / 13.6 / 14.3 / 15.0 m; winter mean Hs 3.6–3.8 m, Tp ~12 s; storm Tp 12.5–20 s. Tp for extremes is assumed.
• Tow tests: 1–8 kn FS → 0.07–0.58 m/s model. Confirm tow method with HWRL.
Sequence per configuration: free decay → regular sweep (s1 first) → irregular operational → extremes/survival.
References: ITTC 7.5-02-07-03.1 (floating offshore platform experiments); IEC TS 62600-103 (WEC testing); DNV-RP-C205 (environmental conditions & loads).
Sources: teamer-us.org/facility/hinsdale-osu ; engineering.oregonstate.edu/facilities/wave-lab/facilities/directional-wave-basin ; Oregon DLCD (2000) Analyses of Extreme Waves and Water Levels (oregon.gov/lcd/Publications/Analysis_ExtremeWaves_WaterLevels_2000.pdf) ; Ruggiero, Komar & Allen (2010) Coastal Engineering 57, doi:10.1016/j.coastaleng.2009.12.005
Legend: blue text on yellow = editable input; black = formula. Edit Inputs, wave sets (Y/N), sea states and configurations; totals update automatically.

## Inputs
HSFP 1:50 Test Matrix – Inputs & Assumptions
Blue text on yellow = editable input. Black = formula. Confirm facility values with HWRL staff.
Parameter | Value | Unit | Source / note
Geometric scale factor λ (full / model) | 50 | – | HSFP summary (1/50 scale model)
Target site | ~200 mi W of Seattle | – | User-specified. ≈47.6°N, 127–128°W, Cascadia Basin (seaward of the continental slope)
Site water depth, full scale (approx.) | 2500 | m | APPROXIMATE – Cascadia Basin abyssal depths ~2,500–2,900 m; verify with NOAA bathymetry. Deep water for all test periods.
LWF test water depth (model) | 2.74 | m | Recommended: deepest depth with published high wave capability (1.8 m @ 2.74 m). Site depth cannot be reproduced at 1:50.
LWF equivalent full-scale depth | 137 | m | Waves ≤ ~13 s are fully deep-water at this depth; 14–20 s are near-deep (kd ≈ 1.5–2.9)
DWB water depth (model) | 1.36 | m | OSU DWB page: max water depth 1.36 m
DWB equivalent full-scale depth | 68 | m | Long-period waves are intermediate-depth here – use DWB only for heading / short-crested tests
LWF max regular wave height (model) | 1.8 | m | TEAMER: 1.8 m at 2.74 m depth. Long-period stroke limit may be lower – confirm with HWRL
DWB max regular wave height (model) | 0.8 | m | TEAMER/OSU: ~0.8 m at 1.37 m depth
Regular wave steepness level 1 (H/L) – linear | 0.016667 | – | Linear RAO level
Regular wave steepness level 2 (H/L) | 0.033333 | – | Moderate – linearity check
Regular wave steepness level 3 (H/L) – steep | 0.066667 | – | Nonlinear / steep
Regular waves recorded per run | 30 | waves | Assumed; steady-state window before reflections
Ramp-up / reflection-free overhead per run | 60 | s | Assumed
Wait between runs – LWF | 6 | min | ASSUMPTION – confirm with HWRL
Wait between runs – DWB | 10 | min | ASSUMPTION – basin settles slower; confirm with HWRL
Irregular sea-state duration, full scale | 3 | hr | ≥3 hr full scale per ITTC/DNV practice
Free-decay run length | 2 | min | Assumed
Free-decay repeats per DOF | 3 | – | Assumed
Special test run length (tow, transition, focused wave) | 5 | min | Assumed
Effective tank hours per day | 6 | hr | Assumed (excludes setup, calibration, configuration changes)
Gravity g | 9.81 | m/s²
Platform footprint, model | 2.4 | m | HSFP summary (~2.4 m square; slender spars, low solid blockage)
Platform footprint, full scale | 120 | m
Minimum comfortable wavemaker period (model) | 0.7 | s | ASSUMPTION – flags periods below this for HWRL review
Time scale factor √λ | 7.0711 | – | Froude: T_model = T_full / √λ
Force scale factor (λ³ × ρ_sea/ρ_fresh) | 128125 | – | Model tested in fresh water
LWF width | 3.7 | m | TEAMER: LWF 104 m × 3.7 m × 4.6 m
Cross-mode flag window (± full-scale period) | 0.5 | s | Regular periods within this window of a flume cross-mode are flagged
LWF transverse (cross-flume) standing-wave modes at LWF test depth
Mode n (wavelength = 2·width / n) | T model (s) | T full (s) | Excitation for a centred model in head seas
1 | 2.1979 | 15.5416 | Antisymmetric – weakly excited if model is centred and aligned
2 | 1.5396 | 10.8863 | Symmetric – can be excited by scattered/radiated waves; place cross-flume gauges
3 | 1.2569 | 8.8878 | Antisymmetric – weakly excited if model is centred and aligned
4 | 1.0885 | 7.6971 | Symmetric – can be excited by scattered/radiated waves; place cross-flume gauges
Tow-speed conversion (horizontal transport tests)
Full-scale tow speed (knots) | Model speed (m/s)
1 | 0.072747
2 | 0.14549
3 | 0.21824
4 | 0.29099
6 | 0.43648
8 | 0.58198

## Regular_Waves
Regular Wave Set (RAO sweep)
Heights set by steepness × deep-water wavelength (site is deep). Mark Y/N for Full and Reduced sets. Fill natural-period rows after free-decay tests.
T full (s) | T model (s) | L0 deep (m, FS) | L at LWF depth (m, FS) | k·d at LWF depth | Depth regime in LWF | L at DWB depth (m, FS) | L0 / footprint | H s1 FS (m) | H s1 model (m) | H s2 FS (m) | H s2 model (m) | H s3 FS (m) | H s3 model (m) | Levels feasible LWF | Levels feasible DWB | Full set (Y/N) | Reduced set (Y/N) | Run time (min, model) | Flags / notes
4 | 0.56569 | 24.981 | 24.981 | 34.4581 | Deep | 24.981 | 0.20817 | 0.41635 | 0.008327 | 0.8327 | 0.016654 | 1.6654 | 0.033308 | 3 | 3 | Y | N | 1.2828 | Below min comfortable wavemaker period. Short-period limit – check wavemaker quality
5 | 0.70711 | 39.0327 | 39.0327 | 22.0532 | Deep | 39.0324 | 0.32527 | 0.65055 | 0.013011 | 1.3011 | 0.026022 | 2.6022 | 0.052044 | 3 | 3 | Y | Y | 1.3536 | Summer wind sea
6 | 0.84853 | 56.2072 | 56.2071 | 15.3147 | Deep | 56.1992 | 0.46839 | 0.93679 | 0.018736 | 1.8736 | 0.037471 | 3.7471 | 0.074943 | 3 | 3 | Y | N | 1.4243
7 | 0.98995 | 76.5042 | 76.5037 | 11.2517 | Deep | 76.4329 | 0.63753 | 1.2751 | 0.025501 | 2.5501 | 0.051003 | 5.1003 | 0.10201 | 3 | 3 | Y | N | 1.495
8 | 1.1314 | 99.9238 | 99.9181 | 8.615 | Deep | 99.5762 | 0.8327 | 1.6654 | 0.033308 | 3.3308 | 0.066616 | 6.6616 | 0.13323 | 3 | 3 | Y | Y | 1.5657 | Near symmetric flume cross-mode – check cross-flume gauges.
8.5 | 1.2021 | 112.8046 | 112.7892 | 7.6319 | Deep | 112.1473 | 0.94004 | 1.8801 | 0.037602 | 3.7602 | 0.075203 | 7.5203 | 0.15041 | 3 | 3 | Y | N | 1.601 | Near antisymmetric cross-mode – verify model centred. Wavelength ≈ footprint band
9 | 1.2728 | 126.4661 | 126.4292 | 6.8085 | Deep | 125.3167 | 1.0539 | 2.1078 | 0.042155 | 4.2155 | 0.084311 | 8.4311 | 0.16862 | 3 | 3 | Y | N | 1.6364 | Near antisymmetric cross-mode – verify model centred. Wavelength ≈ footprint band
9.5 | 1.3435 | 140.9082 | 140.829 | 6.1123 | Deep | 139.0241 | 1.1742 | 2.3485 | 0.046969 | 4.6969 | 0.093939 | 9.3939 | 0.18788 | 3 | 3 | Y | N | 1.6718 | Wavelength ≈ footprint band
10 | 1.4142 | 156.131 | 155.975 | 5.5188 | Deep | 153.2048 | 1.3011 | 2.6022 | 0.052044 | 5.2044 | 0.10409 | 10.4087 | 0.20817 | 3 | 3 | Y | Y | 1.7071
11 | 1.5556 | 188.9185 | 188.4267 | 4.5683 | Deep | 182.721 | 1.5743 | 3.1486 | 0.062973 | 6.2973 | 0.12595 | 12.5946 | 0.25189 | 3 | 3 | Y | N | 1.7778 | Near symmetric flume cross-mode – check cross-flume gauges.
12 | 1.6971 | 224.8286 | 223.575 | 3.8501 | Deep | 213.3517 | 1.8736 | 3.7471 | 0.074943 | 7.4943 | 0.14989 | 14.9886 | 0.29977 | 3 | 3 | Y | Y | 1.8485 | Winter mean peak period (~12 s)
13 | 1.8385 | 263.8614 | 261.1346 | 3.2964 | Deep | 244.6456 | 2.1988 | 4.3977 | 0.087954 | 8.7954 | 0.17591 | 17.5908 | 0.35182 | 3 | 3 | Y | N | 1.9192
14 | 1.9799 | 306.0168 | 300.7644 | 2.862 | Near-deep / intermediate | 276.241 | 2.5501 | 5.1003 | 0.10201 | 10.2006 | 0.20401 | 20.4011 | 0.40802 | 3 | 3 | Y | N | 1.9899
15 | 2.1213 | 351.2947 | 342.0946 | 2.5163 | Near-deep / intermediate | 307.8701 | 2.9275 | 5.8549 | 0.1171 | 11.7098 | 0.2342 | 23.4196 | 0.46839 | 3 | 3 | Y | Y | 2.0607 | Storm peak periods 12.5–20 s
16 | 2.2627 | 399.6954 | 384.7544 | 2.2373 | Near-deep / intermediate | 339.3489 | 3.3308 | 6.6616 | 0.13323 | 13.3232 | 0.26646 | 26.6464 | 0.53293 | 3 | 3 | Y | N | 2.1314 | Near antisymmetric cross-mode – verify model centred.
17 | 2.4042 | 451.2186 | 428.3949 | 2.0094 | Near-deep / intermediate | 370.5608 | 3.7602 | 7.5203 | 0.15041 | 15.0406 | 0.30081 | 30.0812 | 0.60162 | 3 | 3 | Y | N | 2.2021
18 | 2.5456 | 505.8644 | 472.7041 | 1.821 | Near-deep / intermediate | 401.4399 | 4.2155 | 8.4311 | 0.16862 | 16.8621 | 0.33724 | 33.7243 | 0.67449 | 3 | 3 | Y | N | 2.2728
19 | 2.687 | 563.6329 | 517.4156 | 1.6636 | Near-deep / intermediate | 431.9563 | 4.6969 | 9.3939 | 0.18788 | 18.7878 | 0.37576 | 37.5755 | 0.75151 | 3 | 3 | Y | N | 2.3435
20 | 2.8284 | 624.524 | 562.3106 | 1.5308 | Near-deep / intermediate | 462.104 | 5.2044 | 10.4087 | 0.20817 | 20.8175 | 0.41635 | 41.6349 | 0.8327 | 3 | 2 | Y | Y | 2.4142 | Upper bound (changed from 18 s)
17.9 | 2.5314 | 500.2593 | 468.251 | 1.8383 | Near-deep / intermediate | 398.3681 | 4.1688 | 8.3377 | 0.16675 | 16.6753 | 0.33351 | 33.3506 | 0.66701 | 3 | 3 | N | N | 2.2657 | FloatSim pre-test: heave natural period, moored: buoy 17.7, cluster 18.0, platform 18.1 s FS. Broad peak (zeta ~11 %): the 1 s grid resolves it. The heave RAO peaks later in waves (~18.5-19 s FS). Replace with the measured decay. See FloatSim_Predictions.)
19.6 | 2.7719 | 599.7928 | 544.3427 | 1.5814 | Near-deep / intermediate | 450.0888 | 4.9983 | 9.9965 | 0.19993 | 19.9931 | 0.39986 | 39.9862 | 0.79972 | 3 | 3 | N | N | 2.3859 | FloatSim pre-test: tilt/pitch natural period, moored (operational cords): buoy 18.8, cluster 19.6, platform 20.1 s FS. Sharp peak (zeta ~3-4 %): needs the fine-step band per configuration (FloatSim_Predictions). Replace with the measured decay.
20.6 | 2.9133 | 662.5575 | 589.2619 | 1.4608 | Near-deep / intermediate | 480.0191 | 5.5213 | 11.0426 | 0.22085 | 22.0853 | 0.44171 | 44.1705 | 0.88341 | 3 | 2 | N | N | 2.4566 | FloatSim pre-test: platform tilt 20.1 s FS + 0.5 s, the resonance's upper flank, beyond the 20 s bound. Extend the sweep to ~22 s FS (FloatSim_Predictions).
Wavelengths use Fenton's explicit dispersion approximation (±~1%). 'Levels feasible' counts steepness levels within the facility wave-height limit on Inputs. Depth regime: Deep if kd ≥ π.

## Irregular_Seas
Irregular Sea States (JONSWAP) – Site: ~200 mi west of Seattle
Based on NDBC 46005 (West Washington, deep water) statistics. Refine with a site hindcast (e.g., WW3/WIS) Hs–Tp scatter and environmental contour.
ID | Category | Hs FS (m) | Tp FS (s) | γ (peak) | Spreading | Seeds | Full set (Y/N) | Reduced set (Y/N) | Hs model (m) | Tp model (s) | Est. Hmax model (m) | OK in LWF (1/0) | OK in DWB (1/0) | Hs / Lp (deep) | Run time (min, model) | Basis / purpose
O1 | Summer calm | 1.5 | 8 | 3.3 | Long-crested | 1 | Y | N | 0.03 | 1.1314 | 0.0558 | 1 | 1 | 0.015011 | 26.4558 | Summer monthly means at 46005 ~1.5–2 m – access/maintenance window
O2 | Summer typical | 2 | 10 | 3.3 | Long-crested | 1 | Y | Y | 0.04 | 1.4142 | 0.0744 | 1 | 1 | 0.01281 | 26.4558 | Typical summer operations
O3 | Annual mean | 2.8 | 11 | 3.3 | Long-crested | 1 | Y | N | 0.056 | 1.5556 | 0.10416 | 1 | 1 | 0.014821 | 26.4558 | Approximate annual mean Hs offshore WA
E1 | Winter mean / energy design | 3.7 | 12.5 | 3.3 | Long-crested | 1 | Y | Y | 0.074 | 1.7678 | 0.13764 | 1 | 1 | 0.015167 | 26.4558 | Winter monthly mean Hs 3.6–3.8 m, Tp ~12 s (Allen & Komar / DLCD 2000) – WEC design sea
SW1 | Long swell | 2.5 | 16 | 5 | Long-crested | 1 | Y | N | 0.05 | 2.2627 | 0.093 | 1 | 1 | 0.0062548 | 26.4558 | Distant-storm swell; near long spar natural periods?
SW2 | Very long swell | 3 | 20 | 5 | Long-crested | 1 | Y | N | 0.06 | 2.8284 | 0.1116 | 1 | 1 | 0.0048037 | 26.4558 | Upper period bound of matrix
D1 | Winter storm (ops limit) | 6 | 13 | 3.3 | Long-crested | 2 | Y | N | 0.12 | 1.8385 | 0.2232 | 1 | 1 | 0.022739 | 26.4558 | Frequent winter storm – likely operational limit / transfer ops
X1 | ~Annual max storm | 10 | 15 | 2 | Long-crested | 2 | Y | N | 0.2 | 2.1213 | 0.372 | 1 | 1 | 0.028466 | 26.4558 | Typical yearly maximum at 46005 (≈9–11 m) – ASSUMED, verify
X10 | 10-yr extreme | 12.4 | 16 | 2 | Long-crested | 2 | Y | N | 0.248 | 2.2627 | 0.46128 | 1 | 1 | 0.031024 | 26.4558 | 46005 10-yr Hs 12.4 m (DLCD 2000, Table 1); Tp assumed
X50 | 50-yr extreme | 14.3 | 17 | 2 | Long-crested | 3 | Y | Y | 0.286 | 2.4042 | 0.53196 | 1 | 1 | 0.031692 | 26.4558 | 46005 50-yr Hs 14.3 m (DLCD 2000); Tp assumed
X100 | 100-yr extreme | 15 | 17 | 2 | Long-crested | 3 | Y | N | 0.3 | 2.4042 | 0.558 | 1 | 1 | 0.033243 | 26.4558 | 46005 100-yr Hs 15.0 m (DLCD 2000); Tp assumed (storms 12.5–20 s)
X100L | 100-yr, long Tp | 15 | 19 | 2 | Long-crested | 2 | Y | N | 0.3 | 2.687 | 0.558 | 1 | 1 | 0.026613 | 26.4558 | Tp sensitivity – longer-period extreme
SC1 | Short-crested winter | 3.7 | 12.5 | 3.3 | cos-2s, s=15 | 1 | N | N | 0.074 | 1.7678 | 0.13764 | 1 | 1 | 0.015167 | 26.4558 | DWB only – directional averaging (run via config P3-F)
SC2 | Short-crested extreme | 12.4 | 16 | 2 | cos-2s, s=15 | 2 | N | N | 0.248 | 2.2627 | 0.46128 | 1 | 1 | 0.031024 | 26.4558 | DWB only – directional extreme (run via config P3-F)
Hmax ≈ 1.86·Hs (Rayleigh, ~1000 waves). Hs/Lp above ~1/15 is unrealistically steep.
Wave climate is trending upward in the PNW (~0.015 m/yr mean; ~0.071 m/yr for the largest storms, Ruggiero et al. 2010) – consider a margin on the 100-yr Hs for design life.
NDBC 46005 is several hundred km offshore; conditions ~200 mi W of Seattle are similar but a site-specific hindcast should replace these values before final design.

## Configurations
Test Configurations by Phase
Each row = one model configuration. Full matrix on baselines; reduced sets on variants. Run counts and tank time are computed.
Phase | Config ID | Description | Facility (LWF/DWB) | Wave headings | Regular set | Irregular set | Decay DOFs | Special runs | Decay runs | Regular runs | Irregular runs | Total runs | Tank hours | Notes
1 | P1-A | Single spar, vertical, baseline (no fins) | LWF | 1 | Full | Full | 3 | 0 | 9 | 57 | 20 | 86 | 19.4535 | Heave, pitch, surge decay
1 | P1-B | Single spar, vertical, damping fins | LWF | 1 | Reduced | Reduced | 3 | 0 | 9 | 18 | 5 | 32 | 6.2521 | Fin effectiveness vs P1-A
1 | P1-C | Single spar, horizontal (transport) | LWF | 1 | Reduced | None | 3 | 12 | 9 | 18 | 0 | 39 | 5.7475 | Special: tow at 4 speeds × 3 repeats (see Inputs tow table)
1 | P1-D | Single spar, ballast transition H→V | LWF | 1 | None | None | 0 | 9 | 0 | 0 | 0 | 9 | 1.65 | Special: transition in calm + O1 + O2, 3 repeats each
1 | P1-E | Single spar + simulated WEC PTO | LWF | 1 | Reduced | Reduced | 1 | 0 | 3 | 18 | 5 | 26 | 5.4521 | Repeat with 2–3 PTO damping settings if time allows
2 | P2-A | 4-spar cluster, vertical, baseline | LWF | 1 | Full | Full | 4 | 0 | 12 | 57 | 20 | 89 | 19.8535 | Collective behaviour; ball-joint loads
2 | P2-B | 4-spar cluster, damping fins | LWF | 1 | Reduced | Reduced | 3 | 0 | 9 | 18 | 5 | 32 | 6.2521
2 | P2-C | 4-spar cluster, horizontal / transition | LWF | 1 | Reduced | None | 2 | 12 | 6 | 18 | 0 | 36 | 5.3475 | Special: tow + transition runs
2 | P2-D | Cluster at 45° to waves | LWF | 1 | Reduced | Reduced | 0 | 0 | 0 | 18 | 5 | 23 | 5.0521 | Heading sensitivity in flume
3 | P3-A | Full 4-cluster platform, baseline, head seas | LWF | 1 | Full | Full | 5 | 0 | 15 | 57 | 20 | 92 | 20.2535 | Near-deep depth; slender spars → low blockage. Cross-flume gauge pair; watch periods flagged on Regular_Waves
3 | P3-B | Full platform + simulated WEC PTOs | LWF | 1 | Reduced | Reduced | 1 | 0 | 3 | 18 | 5 | 26 | 5.4521
3 | P3-C | Full platform, alternate damping / ballast | LWF | 1 | Reduced | Reduced | 3 | 0 | 9 | 18 | 5 | 32 | 6.2521
3 | P3-D | Full platform, survival focused waves | LWF | 1 | None | None | 0 | 8 | 0 | 0 | 0 | 8 | 1.4667 | Special: focused/breaking wave groups for peak joint loads, slamming
3 | P3-E | Full platform, oblique headings (0°, 22.5°, 45°) | DWB | 3 | Reduced | Reduced | 0 | 0 | 0 | 51 | 15 | 66 | 19.1357 | 0° repeats P3-A at truncated depth → quantifies depth effect; 45° diagonal (~3.4 m) too wide for flume
3 | P3-F | Full platform, short-crested seas | DWB | 2 | None | None | 0 | 6 | 0 | 0 | 0 | 6 | 1.5 | Special: SC1 + SC2 (seeds) × 2 headings

## FloatSim_Predictions
FloatSim pre-test predictions - flume mooring study (HSP repo, studies/flume-mooring)
Pre-test predictions, to be replaced by the measured free decays. Model scale in fresh water; full scale = model x √λ (Inputs!B4). FloatSim LEVEL1, linear hydrodynamics, Morison drag. The flume BEM's 12-sided waterline makes periods long; converged values per DESIGN-BASIS C8. Pitch inputs (CoG, inertia) are unmeasured: ±3 % (DESIGN-BASIS Phase I).
1. Natural periods (heave, tilt/pitch)
Article | Mode | Mooring | Flume BEM T (model s) | Converged T (model s) | Converged T (full scale s) | ζ (FloatSim, H = 0.04 m) | Half-power band (model s) | Basis
Single buoy | heave | free | 2.561 | 2.519 | 17.812 | 11.1% | 0.604 | converged value computed (DESIGN-BASIS C8)
Single buoy | heave | moored, operational cords | 2.548 | 2.508 | 17.7342 | 11.1% | 0.604 | converged value estimated: the C8 mesh shift of this article's earlier moored design
Single buoy | pitch | free | 2.761 | 2.684 | 18.9787 | 4.2% | 0.217 | converged value computed (DESIGN-BASIS C8)
Single buoy | pitch | moored, operational cords | 2.723 | 2.661 | 18.8161 | 4.2% | 0.217 | converged value estimated: the C8 mesh shift of this article's earlier moored design
Cluster (4 buoys) | heave | free | 2.586 | 2.544 | 17.9888 | 11.3% | 0.625 | converged value estimated: the C8 mesh shift of this article's earlier moored design
Cluster (4 buoys) | heave | moored, operational cords | 2.584 | 2.542 | 17.9747 | 11.3% | 0.625 | converged value estimated: the C8 mesh shift of this article's earlier moored design
Cluster (4 buoys) | heave | moored, extreme cords | 2.583 | 2.542 | 17.9747 | 11.3% | 0.625 | converged value estimated: the C8 mesh shift of this article's earlier moored design
Cluster (4 buoys) | tilt | free | 2.856 | 2.792 | 19.7424 | 3.6% | 0.185 | converged value estimated: the C8 mesh shift of this article's earlier moored design
Cluster (4 buoys) | tilt | moored, operational cords | 2.835 | 2.772 | 19.601 | 3.6% | 0.185 | converged value estimated: the C8 mesh shift of this article's earlier moored design
Cluster (4 buoys) | tilt | moored, extreme cords | 2.748 | 2.685 | 18.9858 | 3.6% | 0.185 | converged value estimated: the C8 mesh shift of this article's earlier moored design
4x4 platform | heave | free | 2.599 | 2.557 | 18.0807 | 10.3% | 0.574 | converged value estimated: the C8 mesh shift of this article's earlier moored design
4x4 platform | heave | moored, operational cords | 2.598 | 2.556 | 18.0736 | 10.3% | 0.574 | converged value estimated: the C8 mesh shift of this article's earlier moored design
4x4 platform | heave | moored, extreme cords | 2.598 | 2.555 | 18.0666 | 10.3% | 0.574 | converged value estimated: the C8 mesh shift of this article's earlier moored design
4x4 platform | tilt | free | 2.926 | 2.864 | 20.2515 | 3% | 0.161 | converged value estimated: the C8 mesh shift of this article's earlier moored design
4x4 platform | tilt | moored, operational cords | 2.904 | 2.842 | 20.096 | 3% | 0.161 | converged value estimated: the C8 mesh shift of this article's earlier moored design
4x4 platform | tilt | moored, extreme cords | 2.799 | 2.737 | 19.3535 | 3% | 0.161 | converged value estimated: the C8 mesh shift of this article's earlier moored design
ζ and the half-power band: FloatSim regular-wave sweeps at H = 0.04 m model with the earlier (pin-level) mooring (resonance_bandwidth.json). They grow with wave height (cluster tilt ζ 6.4 % at H = 0.12 m).
In waves the heave RAO peaks later than the decay period: ~2.65-2.70 s model on the flume BEM (≈ 18.5-19 s FS after the mesh correction).
2. Moored slow modes (MOORING-SPEC rev D §5) and the decay record they need
Article | Cord set | Surge T (model s) | Sway T (model s) | Yaw T (model s) | Surge T (full scale s) | Sway T (full scale s) | Record for 5 cycles of the slowest soft mode (model min) | Note
Single buoy | one set | 16.56 | 26.39 | 1.12 | 117.0969 | 186.6055 | 2.2 | yaw is stiff (collar)
Cluster (4 buoys) | operational | 23.13 | 51.63 | 24.78 | 163.5538 | 365.0792 | 4.3
Cluster (4 buoys) | extreme | 10.49 | 28.24 | 18.75 | 74.1755 | 199.687 | 2.4
4x4 platform | operational | 22.92 | 60.76 | 32.72 | 162.0689 | 429.6381 | 5.1
4x4 platform | extreme | 9.91 | 31.05 | 17.09 | 70.0743 | 219.5567 | 2.6
The matrix's free-decay run is 2 min (Inputs!B21). The moored sway and yaw decays need up to ~5 min. The slow modes are also where irregular seas drive slow drift, which FloatSim does not model.
3. Recommended fine-step tilt band per configuration (centre = converged moored tilt, ± 0.20 s model, 0.05 s model steps; ≥ 95 % of the peak)
Configuration | Centre T (model s) | Band periods (model s) |  |  | Band periods (full scale s) |  |  | Note
Single buoy, operational cords | 2.661 | 2.46, 2.51, 2.56, 2.61, 2.66, 2.71, 2.76, 2.81, 2.86 |  |  | 17.4, 17.8, 18.1, 18.5, 18.8, 19.2, 19.5, 19.9, 20.2 |  |  | Re-centre on the measured free decay. Heights: add constant small levels (0.02 and 0.04 m model) to stay near-linear at resonance.
Cluster (4 buoys), operational cords | 2.772 | 2.57, 2.62, 2.67, 2.72, 2.77, 2.82, 2.87, 2.92, 2.97 |  |  | 18.2, 18.5, 18.9, 19.2, 19.6, 20.0, 20.3, 20.7, 21.0 |  |  | Re-centre on the measured free decay. Heights: add constant small levels (0.02 and 0.04 m model) to stay near-linear at resonance.
4x4 platform, operational cords | 2.842 | 2.64, 2.69, 2.74, 2.79, 2.84, 2.89, 2.94, 2.99, 3.04 |  |  | 18.7, 19.0, 19.4, 19.7, 20.1, 20.4, 20.8, 21.2, 21.5 |  |  | Re-centre on the measured free decay. Heights: add constant small levels (0.02 and 0.04 m model) to stay near-linear at resonance.